## Summary
Project Name | Worcester Medical Office Renovation
Application Number | 004
Application Date
Original Contract Sum | 245000
Net Change Orders | 5000
Contract Sum To Date | 250000
Total Completed and Stored | 91000
Retainage | 4550
Previous Certificates for Payment | 30000
Current Payment Due | 57000
Balance to Finish | 159000

## Schedule
Item Number | Description | Scheduled Value | Previous Applications | Work Completed This Period | Materials Presently Stored | Total Completed and Stored to Date | Balance to Finish
001 | General conditions | 100000 | 30000 | 15000 | 5000 | 50000 | 50000
002 | Electrical rough-in | 75000 | 10000 | 12000 | 3000 | 25000 | 50000
003 | Mechanical equipment | 50000 | 0 | 10000 | 0 | 12000 | 38000
003 | Closeout and commissioning | 25000 | 0 | 4000 | 0 | 4000 | 21000